## Test plan
Project name : "Online store"
Target: - Evaluation of the work product - its requirements, user stories and design - Verification of compliance of the product results with the specified requirements - Identification and prevention of failures and defects | Entry Criteria | Exit Criteria | Team
Areas to be tested user registration and authorization, searching and filtering products in the catalog, adding products to the basket, creating orders, paying for orders (with verification of integration with payment systems), checking data validation (for example, registration and authorization forms), checking work with different user roles (authorized and unauthorized user). Areas excluded from testing | - All requirements are described - Test cases and test suites are written - Test environment is configured - Development of the corresponding functionality or module is completed | - All planned tests have been completed. - All critical and high priority defects have been resolved and the remaining defects are within acceptable risk. | 3 testers: - 1 tester (full time) - 1 tester (0.5 time) - 1 trainee tester
Test strategy Functional testing - checking all key functions - Usability testing - checking user interaction with the system (ease of navigation, intuitiveness of the interface) - Security testing - checking compliance with GDPR requirements (e.g. encryption of user data) and testing for vulnerabilities (SQL injections, XSS). - API testing - checking the functionality of the REST API for interaction with the server (authentication, managing cart and order data, integration with the database and payment systems) - Cross-browser and cross-platform testing - checking the application in popular browsers (Chrome, Firefox, Safari, Edge) and on different operating systems (Windows, macOS, Linux, Android, iOS). - Stress testing and load testing - checking the application under a load of 1000 users per minute and testing behavior under peak loads. - Regression testing - performing automated tests to check that new functionality does not disrupt existing functionality - Web and mobile testing - GUI testing - checking the visual and technical aspects of the graphical interface (correct placement of elements, display of fonts, colors, images and icons) | Risks 1 tester will be on vacation for 2 weeks (0.5 of the time allocated for the project) - 1 intern - has little expertise - the development team has not worked on the project yet - the project period is 1 month | Resources PCs and laptops with various operating systems: Windows (the latest 2 versions, such as Windows 10, 11). macOS (the latest 2 versions, such as macOS Monterey, Ventura). Linux (for example, Ubuntu). - Smartphones and tablets with various OS: Android (versions 11 and above, including devices from Samsung, Xiaomi, Google Pixel, etc.), iOS (versions 15 and above, including iPhone and iPad). - Web browsers on PC: Google Chrome, Mozilla Firefox, Microsoft Edge, Safari (only on macOS). - Testing tools: Postman, JMeter Mobile browsers: Chrome (Android), Safari (iOS) - Test data including: products with different characteristics (sizes, prices, discounts) and user accounts.